## ProductBacklog
Exemple d'utilisation de SCRUM- Un déménagement
En vert : complété par Product Owner / En jaune: complété par l'équipe de développement
Id | Titre | User story | Critère d'acceptation | Priorité | Estimation | Statut
1 | Vendre la maison | En tant que membre de la famille (le père), je veux pouvoir contacter des agences immobilières afin de vendre la maison | Trouver une agence immobilière qui répond au critère budget avec une multitude d'offres | 1 | 10 | Non démaré

## SprintBacklog
| Sprint 1 | Start date | 2018-01-14
| Exemple d'utilisation de SCRUM- Un déménagement | End date (included) | 2018-01-26
|  | Initial Scrum Effort | 75
|  | Sprint objectives | établir les options pour vendre la maison
ID | Short name | Value/Importance | Initial Estimate | 2008-07-21 | 2008-07-22 | 2008-07-23 | 2008-07-24 | 2008-07-25 | 2008-07-28 | 2008-07-29 | 2008-07-30 | 2008-07-31 | 2008-08-01
En tant que membre de la famille (le père), je veux pouvoir contacter des agences immobilières afin de vendre la maison | 1. Identifier les options pour les agences immobilières | 2 | 10 | 2008-07-21: 10; 2008-07-22: 10
| 2.Identifier le budget pour chaque agence immobilière | 2 | 10 | 2008-07-21: 10; 2008-07-22: 10
| 3. Choisir la meilleur option | 2 | 5 | 2008-07-21: 5
En tant que membre de la famille, je veux pourvoir réparer la maison afin de la vendre | 1. Peindre la maison | 1 | 50 | 10 | 10 | 20 | 50 | 40 | 20 | 10 | 10
|  |  | 75 | 35 | 30 | 20 | 50 | 40 | 20 | 10 | 10 | 0 | 0 | <= Remaining Scrum Units
|  |  | Forecast | 30 | 26.6667 | 23.3333 | 20 | 16.6667 | 13.3333 | 10 | 6.6667 | 3.3333 | 0 | 0
Note on B6: Auteur: Insert here a quick and short descriptive name for the story. Clear enough so that developers understand what we are talking about and clear enough to distinguish it from other stories. Usually 2 to 10 words
Note on C6: Auteur: This is the product owner's importance rating for this story. The higher is the value, the more important is this story. There is no max value, and we tend to avoid to use "priority 1" cause if you later decide that something else is even more important, do you think you would put "priority 0" or "priority -1" ? ?
Note on D6: Auteur: This is the team's initial assessment of how much work is needed to implement this story compared to other stories. The unit is story points and usually corresponds roughly to "ideal man days". The importance is to undertand that this is just a relative value that will be accurate if you compute-it with the Team's velocity. If a team velocity is 3 units / days then you can quickly figure-out when the req might be ready. This part (all green items) must be filled by KARMA developers only. Not by the product owner
Note on D18: Auteur: Initial total of Scrum units
Note on E19: Auteur: Edit this cell formula and make a link to the calculs Sheet so that the graph is generated automatically